## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Group 50 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Tingting Cheng | Yiwen Xue | Wenjun Qian | Zhuheng Wang
Project Start Date: | 2021-09-14 |  |  |  |  | September | [20 empty] | October | [27 empty] | November
Scrolling Increment: | 0 | time axis 2021-09-14 to 2021-11-08
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-09-14 to 2021-11-08
literation 1
literation planning and meeting | Goal | Tingting Cheng | 25% | 2021-09-14 | 1 | 2021-09-14: 2
Complete stakeholder register | High Risk | Yiwen Xue | 100% | 2021-09-15 | 5
Design persona | Low Risk | Yiwen Xue | 50% | 2021-09-20 | 8
Review and test persona | Med Risk | Zhuheng Wang | 75% | 2021-09-24 | 4
Complete progress report | Med Risk | Wenjun Qian | 100% | 2021-09-28 | 2
Milestone 01 | Milestone | Tingting Cheng | 10% | 2021-10-01 | 1
literation 2
literation planning and meeting | Goal | Tingting Cheng | 60% | 2021-10-08 | 1 | 2021-10-08: 2
Complete Gantt chart and resours needs | High Risk | Yiwen Xue | 50% | 2021-10-12 | 1
GitHub boards | Low Risk | Yiwen Xue | 33% | 2021-10-15 | 4
Review and test persona | Med Risk | Zhuheng Wang | 100% | 2021-10-19 | 1
Milestone 02 | Milestone | Wenjun Qian | 10% | 2021-10-20 | 2 | bar: 2021-10-20 to 2021-10-21
literation 3
literation planning and meeting | Goal | Tingting Cheng | 60% | 2021-10-22 | 1 | 2021-10-22: 2
Website intergration and publish | High Risk | Yiwen Xue | 50% | 2021-10-26 | 5
Review and test persona | Med Risk | Zhuheng Wang | 100% | 2021-10-27 | 8
Milestone 03 | Milestone | Wenjun Qian | 10% | 2021-10-28 | 4 | bar: 2021-10-28 to 2021-10-31
Formulas:
Zhuheng Wang = [Zhuheng Wang, row above]+1

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 14/09/2021 |  |  |  |  | October | [20 empty] | November | [27 empty] | December
Scrolling Increment: | 0 | time axis 2021-10-15 to 2021-12-09
Milestone description | Category | Assigned to | Progress | Start | Days | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
TITLE 1
Task 1 | Goal | Name | 25% | 2021-10-15 | 3 | F: 2; S: 2; S: 2
Task 2 | Milestone |  |  | 2021-10-20 | 1 | bar: W
Task 3 | Low Risk |  | 50% | 2021-10-12 | 10
Task 4 | Milestone |  |  | 2021-11-04 | 1 | bar: T
Task 5 | Med Risk |  | 10% | 2021-10-21 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-10-21 | 13
Task 2 | On Track |  | 50% | 2021-10-23 | 9
Task 3 | Low Risk |  | 33% | 2021-10-28 | 11
Task 4 | Milestone |  |  | 2021-10-30 | 1 | bar: S
Task 5 |  |  |  | 2021-10-31 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-10-30 | 4
Task 2 | Med Risk |  |  | 2021-11-02 | 14
Task 3 | On Track |  |  | 2021-11-17 | 6
Task 4 | Goal |  |  | 2021-11-21 | 3 | S: 2; M: 2; T: 2
Task 5 | Low Risk |  |  | 2021-10-21 | 19
TITLE 4
Task 1 |  |  |  | 2021-11-24 | 15
Task 2 |  |  |  | 2021-12-08 | 5
Task 3 | Milestone |  |  | 2022-01-19 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-10-15 |  |  |  |  | October | [20 empty] | November | [27 empty] | December
Scrolling Increment: | 0 | time axis 2021-10-15 to 2021-12-09
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-10-15 to 2021-12-09
TITLE 1
Task 1 | Goal | Name | 25% | 2021-10-15 | 3 | 2021-10-15: 2; 2021-10-16: 2; 2021-10-17: 2
Task 2 | Milestone |  |  | 2021-10-20 | 1 | bar: 2021-10-20
Task 3 | Low Risk |  | 50% | 2021-10-12 | 10
Task 4 | Milestone |  |  | 2021-11-04 | 1 | bar: 2021-11-04
Task 5 | Med Risk |  | 10% | 2021-10-21 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-10-21 | 13
Task 2 | On Track |  | 50% | 2021-10-23 | 9
Task 3 | Low Risk |  | 33% | 2021-10-28 | 11
Task 4 | Milestone |  |  | 2021-10-30 | 1 | bar: 2021-10-30
Task 5 |  |  |  | 2021-10-31 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-10-30 | 4
Task 2 | Med Risk |  |  | 2021-11-02 | 14
Task 3 | On Track |  |  | 2021-11-17 | 6
Task 4 | Goal |  |  | 2021-11-21 | 3 | 2021-11-21: 2; 2021-11-22: 2; 2021-11-23: 2
Task 5 | Low Risk |  |  | 2021-10-21 | 19
TITLE 4
Task 1 |  |  |  | 2021-11-24 | 15
Task 2 |  |  |  | 2021-12-08 | 5
Task 3 | Milestone |  |  | 2022-01-19 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one